## Sheet1
High-Level Project Schedule
| 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | Remarks
Description of Task/Milestones
Weekly Document Revisions
UML Diagrams
Coding
Current Weather | [7 empty] | Will be a continous work in progress as different weather occurs over time that needs to be caught
Parameter List | [7 empty] | Get the parameter in a database and onto the main page
Select Closing Parameters | [7 empty] | Have the ability for a user to select the parameters and to have them display in a chart on the main page
Admin Panel | [7 empty] | Have the user be able to select what to display on the front page
FAQ Page
User account | [7 empty] | Have the admin be able to use the page without anyone changing it
User enters forecast | [7 empty] | Have the user be able to enter a forecast and display it on the main page
Start page of some sort possibly | [7 empty] | Look into possibly a start page for setting up database. Would happen if user is using an account.
Maybes
Have a list of severe weather alerts on main page | [7 empty] | Only valid for local area
Throughout Project and towards End Tasks
Testing
Project Presentation