## Sheet1
Schedule for rest of semester
Week | Task
Jan 18th-24th | Work on getting user forecast input and the numbers associated with the weights working together to make a decision
Jan 25th – 31st | Fix the gui on the home screen for the weights and make it look better
Feb 1st – 7th | Work on having the user select what to have output on the home screen
Feb 8th – 14th | Work on having the user select parameters and weights associated for an output on the home screen
Feb 15th – 21st | Work on the gui for all the pages associated with the site
Feb 22nd – 28th | Work on a start screen for a user who may not have a database set up and to get all the databases populated
Throughout semester | Make sure the current weather is working properly
Most likely to remove from project:
System being able to generate a forecast by calculating the numbers from the associated data